## Sheet1
| Week 1 | Week 2 | Week 3 | Week 4 | Last days
Anmol Dura | Brand definition, Hotel Name and colour palette Definition, Tasks distribution. Website Structure. | Template html and css creation. | CSS stylesheet. Home Webpage, Our-Group page html and css. Created Hamburger manu for the mobile viewport. | CSS code to style Home Webpage for Tablet and Desktop Viewport, created wireframe for home page using the existing service page wireframe. | Review final details, Validate all codes html and css on validator. links and final document.
Aarati Thapa |  | About Us html research and code | CSS code to style About Us Webpage for Mobile Viewport | CSS code to style About Us Webpage for Tablet and Desktop Viewport.
Madhavi Neupane |  | Booking and Contact html research and code | CSS code to style Contact Webpage for Mobile Viewport | CSS code to style Contact Webpage for Tablet and Desktop Viewport.
Juan Gustavo Garcia Echeverry |  | Logo Creation. Amenities html research and code | CSS code to style Amenities Webpage for Mobile Viewport | CSS code to style Amenities Webpage for Tablet and Desktop Viewport.
Maria Isabel Meléndez Torres |  | Services and Events html research and code. Site Map on Draw app. | CSS code to style Services and Events Webpage for mobile viewport. | CSS code to style Services and Events Webpage for Tablet and Desktop viewport. Word Document.